Consultation Plan 


Project:
Draft Report “An Assessment of Traffic Impacts Upon Kensington and Parts of Kingsford”
File Reference:

F2009/00234
Purpose of consultations:


· To inform residents about the contents of the report,  and the proposed current or future changes in the Kensington/West Kingsford area which may influence traffic and transport.
· To seek residents views on the draft report.
Impact Level:

Local higher level 

City lower level
Level of consultation:
Consult
Stakeholder groups:

· Residents in west Kensington and west Kingsford
· Kensington Precinct & Kensington Traffic Sub Committee
· Kensington Chamber of Commerce

· Kingsford Chamber of Commerce
Council reports / resolutions:
Listed on Extranet and in Library folder
Consultation activities:

	Activity


	Dates
	Notes

	Public release of report through Committee business papers
	7 July 09
	Agenda

	Briefing to precinct meeting
	13 July
	Consultant and Council staff

	Council Committee meeting
	14 July
	TL to attend

	Develop explanatory flyer
	17 July 
	Distributed to residents, the precincts and chambers, go on website and extranet and at libraries and Customer Services.

	RCC website page - Community Consultation page
	17 July
	Report and link to extranet site



	www.kensotraffic.com.au
	17 July
	All documentation to be updated

	Library folder at:

· Bowen Library

· Customer Service Desk
	20 July
	Feedback form to be provided for comments

	Email advice to:

· Kenso precinct 

· Kenso Chamber

· Kingsford Chamber

· All precincts

· All chambers
	20 July
	

	Letter box flyer to all residents in study area
	20 July
	Kensington residents

	Southern Courier advertisement
	21 July
	Deadline for copy to Comms – 14 July. 

Exhibition period: 21 July – 14 Aug 09

	Media release and ‘What’s hot’
	21 July
	

	Mayor’s Column
	28 July
	


